## Welcome & How To Use
THE RENOVATION & REPAIR RECORD BOOK — DIGITAL COMPANION
Free with the printed book, by @Antz · LogicManse Publications · https://www.logicmanse.ca/RenovationRepairLog
HOW THIS PAIRS WITH THE PRINTED BOOK
This workbook covers the same ground as the paperback — properties, projects, contractor quotes, permits, budgets, materials, and photo logs — but it does the adding up for you. Keep the book for a paper trail you can hand a contractor, inspector, or accountant; use this workbook when you want a running total without reaching for a calculator.
HOW TO USE THIS WORKBOOK
• Set up once per property — fill in Portfolio Summary and Project Tracker when you start a property or project; you'll rarely touch either again for that row.
• Every log tab points back to Project Tracker — use the Project dropdown on Contractor & Quote Comparison, Permit & Inspection Tracker, Budget vs. Actual, Materials & Product Reference, Photo Log, and Contractor Performance Review, rather than retyping the project name.
• Log a quote the day you get it — Contractor & Quote Comparison, one row per quote, so a comparison made months apart still reads the same way.
• Log an expense as it happens — Budget vs. Actual, one line per line item, the day the money moves, not at tax time.
• Renovation Spend by Property adds itself up — it reads every row of Budget vs. Actual automatically; nothing there needs to be typed.
• Repair vs. Capital Improvement Reference is a record, not an answer — exactly like the printed page it mirrors, it exists to hold what your own accountant or tax authority told you, never a guess made while the invoice is still on the counter.
• Check Key Dates and Seasonal Maintenance monthly — a five-second glance catches a permit deadline or an overdue filter change before it's a problem.
Legend: cells shaded pale gray and italic are worked examples — overwrite or clear them. Every other blank cell in this workbook is yours to fill in.

## Portfolio Summary
PROPERTY PORTFOLIO SUMMARY
Free with the printed book, by @Antz · LogicManse Publications · https://www.logicmanse.ca/RenovationRepairLog
One row per property — up to 4. Fill in once; every other tab looks up properties by the name in column A.
Property (nickname or address) | Year built | Roof age | HVAC age | Electrical panel | Water heater age
Maple St Duplex | 1974 | 12 years | 4 years | 100A, updated 2019 | 6 years
Property 2
Property 3
Property 4
Row 5 is a worked example (gray italic) — overwrite it with Property 1's real details, or clear it if you have fewer than 4 properties.

## Portfolio Summary at a Glance
PORTFOLIO SUMMARY AT A GLANCE
Free with the printed book, by @Antz · LogicManse Publications · https://www.logicmanse.ca/RenovationRepairLog
Every number below reads live from the tabs you fill in elsewhere.
Total properties tracked in this book | 4
Total renovation/repair projects logged | 1
Total spend to date (sum of every property's Actual column) | 8950
Projects currently in progress | 1
Projects completed | 0
Projects on hold or deferred | 0
Next project planned, and for which property (fill in by hand)
“Next project planned” has no reliable formula — it depends on your own priorities, not a date field — so it's left as a plain fill-in cell rather than a formula pretending to compute it.

## Project Tracker
PROJECT TRACKER
Free with the printed book, by @Antz · LogicManse Publications · https://www.logicmanse.ca/RenovationRepairLog
Up to 5 renovation or repair projects per property — the anchor every other tab's Project dropdown pulls from.
Property | Project name | Scope (one line) | Target start | Target finish | Status | Project ID (auto — don't edit)
Maple St Duplex | Kitchen refresh | Cabinets, counters, backsplash | 2026-03-01 | 2026-04-15 | In Progress | Maple St Duplex — Kitchen refresh
Row 5 is a worked example. Column G builds automatically from columns A and B — every other tab's Project dropdown reads from column G, so two properties can each have a “Kitchen refresh” without the workbook mixing them up.

## Contractor & Quote Comparison
CONTRACTOR & QUOTE COMPARISON
Free with the printed book, by @Antz · LogicManse Publications · https://www.logicmanse.ca/RenovationRepairLog
One row per quote received — pick the Project from the dropdown.
Project | Contractor | Quote amount | Timeline | References checked? | Selected?
Maple St Duplex — Kitchen refresh | Riverside Kitchens & Cabinetry | 14200 | 5 weeks | Yes | Yes
Row 5 is a worked example. Add more rows the same way if 30 quotes isn't enough — copy a blank row's formatting down.

## Permit & Inspection Tracker
PERMIT & INSPECTION TRACKER
Free with the printed book, by @Antz · LogicManse Publications · https://www.logicmanse.ca/RenovationRepairLog
One row per permit — pick the Project from the dropdown.
Project | Permit type | Date applied | Date issued | Inspection date(s) | Result
Maple St Duplex — Kitchen refresh | Electrical | 2026-02-20 | 2026-03-01 | 2026-04-18 | Pass
Row 5 is a worked example.

## Budget vs. Actual
BUDGET VS. ACTUAL
Free with the printed book, by @Antz · LogicManse Publications · https://www.logicmanse.ca/RenovationRepairLog
One row per line item — pick the Project from the dropdown. Variance calculates itself.
Project | Line item | Budgeted | Actual | Variance | Why
Maple St Duplex — Kitchen refresh | Cabinets & installation | 8500 | 8950 | -450 | Upgraded to soft-close hinges mid-project
Row 5 is a worked example. Column E (Variance = Budgeted − Actual) calculates itself — positive means under budget, negative (shown in parentheses) means over. This tab feeds Renovation Spend by Property automatically.

## Materials & Product Reference
MATERIALS, FIXTURES & PRODUCT REFERENCE
Free with the printed book, by @Antz · LogicManse Publications · https://www.logicmanse.ca/RenovationRepairLog
One row per item — pick the Project from the dropdown.
Project | Item | Brand | Model / colour code | Supplier | Purchase date
Maple St Duplex — Kitchen refresh | Countertop | Caesarstone | Pure White 6131 | Downtown Stone Supply | 2026-03-10
Row 5 is a worked example.

## Photo Log
BEFORE / DURING / AFTER PHOTO LOG
Free with the printed book, by @Antz · LogicManse Publications · https://www.logicmanse.ca/RenovationRepairLog
This workbook logs where each photo lives — it doesn't store images itself. Pick the Project from the dropdown.
Project | Date | Stage (before/during/after) | Filename or album | Note
Maple St Duplex — Kitchen refresh | 2026-03-01 | Before | Photos/MapleKitchen/before_01.jpg | Original 1980s layout, for comparison
Row 5 is a worked example.

## Property Systems & Appliances
PROPERTY SYSTEMS & APPLIANCE REFERENCE
Free with the printed book, by @Antz · LogicManse Publications · https://www.logicmanse.ca/RenovationRepairLog
One block per property — the same 12 systems/appliances repeat for each.
Property | System / appliance | Brand / model | Install date | Expected lifespan | Serviced by
Maple St Duplex | Roof | GAF Timberline HDZ | 2014-09-01 | 25-year shingle | Summit Roofing
Maple St Duplex | Furnace / HVAC system
Maple St Duplex | Water heater
Maple St Duplex | Electrical panel
Maple St Duplex | Refrigerator
Maple St Duplex | Range / oven
Maple St Duplex | Washer
Maple St Duplex | Dryer
Maple St Duplex | Dishwasher
Maple St Duplex | Windows (overall)
Maple St Duplex | Garage door opener
Maple St Duplex | Smoke & CO detectors
Property 2 | Roof
Property 2 | Furnace / HVAC system
Property 2 | Water heater
Property 2 | Electrical panel
Property 2 | Refrigerator
Property 2 | Range / oven
Property 2 | Washer
Property 2 | Dryer
Property 2 | Dishwasher
Property 2 | Windows (overall)
Property 2 | Garage door opener
Property 2 | Smoke & CO detectors
Property 3 | Roof
Property 3 | Furnace / HVAC system
Property 3 | Water heater
Property 3 | Electrical panel
Property 3 | Refrigerator
Property 3 | Range / oven
Property 3 | Washer
Property 3 | Dryer
Property 3 | Dishwasher
Property 3 | Windows (overall)
Property 3 | Garage door opener
Property 3 | Smoke & CO detectors
Property 4 | Roof
Property 4 | Furnace / HVAC system
Property 4 | Water heater
Property 4 | Electrical panel
Property 4 | Refrigerator
Property 4 | Range / oven
Property 4 | Washer
Property 4 | Dryer
Property 4 | Dishwasher
Property 4 | Windows (overall)
Property 4 | Garage door opener
Property 4 | Smoke & CO detectors
Column A fills itself from Portfolio Summary — leave a property's block blank if you have fewer than 4 properties. Row 5 is a worked example.

## Emergency Contacts & Shut-offs
EMERGENCY CONTACTS & UTILITY SHUT-OFFS
Free with the printed book, by @Antz · LogicManse Publications · https://www.logicmanse.ca/RenovationRepairLog
One block per property.
Property | Field | Value
Maple St Duplex | Gas shut-off location | Basement, north wall, next to the meter
Maple St Duplex | Water main shut-off location
Maple St Duplex | Electrical panel location
Maple St Duplex | Gas utility company & account line
Maple St Duplex | Electric utility company & account line
Maple St Duplex | Water / sewer utility company & account line
Maple St Duplex | Property manager or on-call contact
Maple St Duplex | A 24-hour plumber/electrician on file for this property
Maple St Duplex | Alarm / security company & code holder
Maple St Duplex | Non-emergency police/fire line for this municipality
Property 2 | Gas shut-off location
Property 2 | Water main shut-off location
Property 2 | Electrical panel location
Property 2 | Gas utility company & account line
Property 2 | Electric utility company & account line
Property 2 | Water / sewer utility company & account line
Property 2 | Property manager or on-call contact
Property 2 | A 24-hour plumber/electrician on file for this property
Property 2 | Alarm / security company & code holder
Property 2 | Non-emergency police/fire line for this municipality
Property 3 | Gas shut-off location
Property 3 | Water main shut-off location
Property 3 | Electrical panel location
Property 3 | Gas utility company & account line
Property 3 | Electric utility company & account line
Property 3 | Water / sewer utility company & account line
Property 3 | Property manager or on-call contact
Property 3 | A 24-hour plumber/electrician on file for this property
Property 3 | Alarm / security company & code holder
Property 3 | Non-emergency police/fire line for this municipality
Property 4 | Gas shut-off location
Property 4 | Water main shut-off location
Property 4 | Electrical panel location
Property 4 | Gas utility company & account line
Property 4 | Electric utility company & account line
Property 4 | Water / sewer utility company & account line
Property 4 | Property manager or on-call contact
Property 4 | A 24-hour plumber/electrician on file for this property
Property 4 | Alarm / security company & code holder
Property 4 | Non-emergency police/fire line for this municipality
Column A fills itself from Portfolio Summary. Row 5 is a worked example.

## Seasonal Maintenance Checklist
SEASONAL MAINTENANCE CHECKLIST
Free with the printed book, by @Antz · LogicManse Publications · https://www.logicmanse.ca/RenovationRepairLog
One block per property.
Property | Task | Season due | Done on | Notes
Maple St Duplex | Clean gutters & downspouts | Fall | 2026-10-12
Maple St Duplex | Inspect roof & flashing
Maple St Duplex | Test smoke & CO detectors
Maple St Duplex | Change HVAC filter
Maple St Duplex | Service furnace / AC
Maple St Duplex | Inspect caulking & weatherstripping
Maple St Duplex | Flush water heater
Maple St Duplex | Winterize exterior hose bibs
Maple St Duplex | Inspect foundation & grading
Maple St Duplex | Check sump pump
Maple St Duplex | Inspect exterior paint / siding
Maple St Duplex | Trim trees & shrubs near structure
Property 2 | Clean gutters & downspouts
Property 2 | Inspect roof & flashing
Property 2 | Test smoke & CO detectors
Property 2 | Change HVAC filter
Property 2 | Service furnace / AC
Property 2 | Inspect caulking & weatherstripping
Property 2 | Flush water heater
Property 2 | Winterize exterior hose bibs
Property 2 | Inspect foundation & grading
Property 2 | Check sump pump
Property 2 | Inspect exterior paint / siding
Property 2 | Trim trees & shrubs near structure
Property 3 | Clean gutters & downspouts
Property 3 | Inspect roof & flashing
Property 3 | Test smoke & CO detectors
Property 3 | Change HVAC filter
Property 3 | Service furnace / AC
Property 3 | Inspect caulking & weatherstripping
Property 3 | Flush water heater
Property 3 | Winterize exterior hose bibs
Property 3 | Inspect foundation & grading
Property 3 | Check sump pump
Property 3 | Inspect exterior paint / siding
Property 3 | Trim trees & shrubs near structure
Property 4 | Clean gutters & downspouts
Property 4 | Inspect roof & flashing
Property 4 | Test smoke & CO detectors
Property 4 | Change HVAC filter
Property 4 | Service furnace / AC
Property 4 | Inspect caulking & weatherstripping
Property 4 | Flush water heater
Property 4 | Winterize exterior hose bibs
Property 4 | Inspect foundation & grading
Property 4 | Check sump pump
Property 4 | Inspect exterior paint / siding
Property 4 | Trim trees & shrubs near structure
Column A fills itself from Portfolio Summary. Row 5 is a worked example.

## Contractor Performance Review
CONTRACTOR PERFORMANCE REVIEW
Free with the printed book, by @Antz · LogicManse Publications · https://www.logicmanse.ca/RenovationRepairLog
One row per completed project — pick the Project from the dropdown.
Contractor | Project | Quality (1-5) | On budget? | On time? | Would rehire?
Riverside Kitchens & Cabinetry | Maple St Duplex — Kitchen refresh | 5 | Yes | Yes | Yes
Row 5 is a worked example.

## Vendor & Contractor Directory
VENDOR & CONTRACTOR DIRECTORY
Free with the printed book, by @Antz · LogicManse Publications · https://www.logicmanse.ca/RenovationRepairLog
Your go-to contractor by trade.
Trade | Company / contact name | Phone | Email | Licence # / insurance confirmed (date) | Notes
General Contractor
Roofer
Plumber
Electrician
HVAC Technician
Flooring Installer
Painter
Landscaper
Handyman
Window & Door Installer
Insulation Contractor
Waste & Junk Removal
Appliance Repair Technician
Pest Control
Locksmith
Pool / Spa Service
Chimney Sweep
Septic Service
Well & Water Treatment
Foundation / Waterproofing
Fence & Deck Contractor
Garage Door Technician
Property Manager / Superintendent
Cleaning Service

## Renovation Spend by Property
RENOVATION SPEND BY PROPERTY
Free with the printed book, by @Antz · LogicManse Publications · https://www.logicmanse.ca/RenovationRepairLog
Every dollar in Budget vs. Actual, rolled up by property — fully automatic.
Property | Total budgeted (all projects) | Total actual | Variance | Share of portfolio spend
Maple St Duplex | 8500 | 8950 | -450 | 100%
Property 2 | 0 | 0 | 0 | 0%
Property 3 | 0 | 0 | 0 | 0%
Property 4 | 0 | 0 | 0 | 0%
PORTFOLIO TOTAL | 8500 | 8950 | -450
Matches each property's rows in Budget vs. Actual by the “Property — Project” text its Project column stores, so nothing here needs to be typed twice.

## Capital Improvements Log
CAPITAL IMPROVEMENTS RUNNING LOG
Free with the printed book, by @Antz · LogicManse Publications · https://www.logicmanse.ca/RenovationRepairLog
Portfolio-wide, for tax time — what your accountant told you, not a guess.
Property | Date | Description | Amount | Classification | Notes
Maple St Duplex | 2026-04-15 | Kitchen refresh — full cabinet & counter replacement | 14200 | Capital improvement (confirmed by accountant, 2026-04-20) | See Repair vs. Capital Improvement Reference tab
Row 5 is a worked example. Classification is always a transcription of what your accountant or tax authority actually said — see the Repair vs. Capital Improvement Reference tab.

## Annual Budget Planner
ANNUAL RENOVATION BUDGET PLANNER
Free with the printed book, by @Antz · LogicManse Publications · https://www.logicmanse.ca/RenovationRepairLog
Forward planning, one row per property per year — four years of runway.
Year | Property | Planned project | Estimated cost | Priority (1-3)
Year 1 | Maple St Duplex | Roof replacement | 16000 | 1
Year 1 | Property 2
Year 1 | Property 3
Year 1 | Property 4
Year 2 | Maple St Duplex
Year 2 | Property 2
Year 2 | Property 3
Year 2 | Property 4
Year 3 | Maple St Duplex
Year 3 | Property 2
Year 3 | Property 3
Year 3 | Property 4
Year 4 | Maple St Duplex
Year 4 | Property 2
Year 4 | Property 3
Year 4 | Property 4
Column B fills itself from Portfolio Summary. Row 5 is a worked example. Priority 1 = most urgent.

## Repair vs Capital Reference
REPAIR VS. CAPITAL IMPROVEMENT REFERENCE
Free with the printed book, by @Antz · LogicManse Publications · https://www.logicmanse.ca/RenovationRepairLog
A record of what you were told, not a ruling — see “Repair or Capital Improvement?” in the printed book.
Category | My tax authority's classification | Told by (name/firm) | Date confirmed
Roof
Furnace / HVAC system
Flooring
Kitchen
Bathroom
Windows & doors
Plumbing
Electrical
Paint & finishes
Landscaping & exterior
Structural / foundation
Appliances
This tab is deliberately blank until your own accountant or tax authority tells you a classification — the book and this workbook never calculate or imply one.